## Gantt Chart
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | PCT OF TASK COMPLETE | PHASE ONE (Initiation and Project Proposal Planning) | [20 empty] | PHASE TWO (Progress Report 1) | [27 empty] | PHASE 3 (Progress Report 2) | [20 empty] | PHASE 4 (Final Code, Report, and Presentation)
[6 empty] | WEEK 1 (Jan. 9 - 15) | [6 empty] | WEEK 2 (Jan. 16 - 22) | [6 empty] | WEEK 3 (Jan. 23 - 29) | [6 empty] | WEEK 4 (Jan. 30 - Feb. 5) | [6 empty] | WEEK 5 (Feb. 6 - 12) | [6 empty] | WEEK 6 (Feb. 13 - 19) | [6 empty] | WEEK 7 (Feb. 20 - 26) | [6 empty] | WEEK 8 (Feb. 27 - Mar. 5) | [6 empty] | WEEK 9 (Mar. 6 - 12) | [6 empty] | WEEK 10 (Mar. 13 - 19) | [6 empty] | WEEK 11 (Mar. 20 - 26) | [6 empty] | WEEK 12 (Mar. 27 - Apr. 2) | [6 empty] | Week 13 (Apr. 3 - 9) | [6 empty] | Week 13 (Apr. 10 - 16)
[6 empty] | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S
1 | Project Initiation and Planning
1.1 | Group creation | All | 2022-01-12 | 2022-01-13 | 100% | bar: WEEK 1 (Jan. 9 - 15) S; WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
1.2 | Group meeting | All | 2022-01-15 | 2022-01-15 | Ongoing | bar: WEEK 1 (Jan. 9 - 15) S; WEEK 2 (Jan. 16 - 22) M; WEEK 2 (Jan. 16 - 22) S; WEEK 3 (Jan. 23 - 29) M; WEEK 4 (Jan. 30 - Feb. 5) M; WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S; WEEK 5 (Feb. 6 - 12) M; WEEK 5 (Feb. 6 - 12) S
1.3 | Meeting with project partner | S, M, F, W | 2022-01-20 | 2022-02-20 | Ongoing | bar: WEEK 2 (Jan. 16 - 22) R; WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S; WEEK 6 (Feb. 13 - 19) M
1.4 | Outline tasks and assign roles | S, M, F, W | 2022-01-24 | 2022-01-27 | 100% | bar: WEEK 2 (Jan. 16 - 22) S to WEEK 4 (Jan. 30 - Feb. 5) S
1.5 | Gantt Chart | W, M, F | 2022-01-24 | 2022-01-29 | 100% | bar: WEEK 3 (Jan. 23 - 29) M to WEEK 3 (Jan. 23 - 29) R; WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
1.6 | PPT Presentation | S, M, F, W | 2022-01-29 | 2022-02-10 | 100% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 5 (Feb. 6 - 12) W
1.7 | Project Proposal | All | 2022-01-22 | 2022-02-08 | 95% | bar: WEEK 2 (Jan. 16 - 22) S to WEEK 4 (Jan. 30 - Feb. 5) S
2 | Understanding Data (Progress Report 1)
2.1 | Data Wrangling | Y, S, W, M | 2022-01-08 | 2022-02-12 | 100% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 8 (Feb. 27 - Mar. 5) M
2.2 | Data Cleaning I | Y, S, W, M | 2022-02-08 | 2022-02-15 | 100% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 8 (Feb. 27 - Mar. 5) M
2.3 | Data Analysis (EDA) | Y, S, W, M | 2022-02-08 | 2022-03-17 | 80% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
2.4 | Progress Report 1 | F, S, W | 2022-02-09 | 2022-03-17 | 100% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3 | Project Implementation (Progress Report 2)
3.1 | Data Cleaning II | Y, W | 2022-03-01 | 2022-03-25 | 50% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3.2 | Data Preparation | S, F | 2022-03-14 | 2022-03-21 | 50% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3.3 | Forecasting Model | M, W | 2022-03-16 | 2022-03-30 | 10% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3.4 | Model Evaluation | S, M | 2022-03-16 | 2022-03-31 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3.5 | User testing and GUI | M | 2022-03-24 | 2022-04-04 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3.6 | Progress Report 2 | F | 2022-02-14 | 2022-03-31 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
4 | Final Code, Report, and Presentation
4.1 | Modify project based on feedback |  | 2022-03-18 | 2022-04-04 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
4.2 | Report + Presentation |  | 2022-03-19 | 2022-04-11 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
4.3 | Code + User-guide |  | 2022-03-20 | 2022-04-14 | 25% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S

## Copy of Gantt Chart
GANTT CHART
PROJECT TITLE |  | Econ 599.88 - KPI Prediction Tool: A Look Into The Future |  |  |  |  | ORGANIZATION NAME | [9 empty] | Critical Mass (CM)
PROJECT MEMBERS |  | Feyre Gezahegn, Wes Warman, Muhammad Khan, Saul Chirinos, Yutong Liu |  |  |  |  | ORGANIZATION CONTACT | [9 empty] | Gunpreet Singh (gunpreets@criticalmass.com)
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | PCT OF TASK COMPLETE | PHASE ONE (Initiation and Project Proposal Planning) | [20 empty] | PHASE TWO (Progress Report 1) | [27 empty] | PHASE 3 (Progress Report 2) | [20 empty] | PHASE 4 (Final Code, Report, and Presentation)
[6 empty] | WEEK 1 (Jan. 9 - 15) | [6 empty] | WEEK 2 (Jan. 16 - 22) | [6 empty] | WEEK 3 (Jan. 23 - 29) | [6 empty] | WEEK 4 (Jan. 30 - Feb. 5) | [6 empty] | WEEK 5 (Feb. 6 - 12) | [6 empty] | WEEK 6 (Feb. 13 - 19) | [6 empty] | WEEK 7 (Feb. 20 - 26) | [6 empty] | WEEK 8 (Feb. 27 - Mar. 5) | [6 empty] | WEEK 9 (Mar. 6 - 12) | [6 empty] | WEEK 10 (Mar. 13 - 19) | [6 empty] | WEEK 11 (Mar. 20 - 26) | [6 empty] | WEEK 12 (Mar. 27 - Apr. 2) | [6 empty] | Week 13 (Apr. 3 - 9) | [6 empty] | Week 13 (Apr. 10 - 16)
[6 empty] | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S
1 | Project Initiation and Planning
1.1 | Group creation | All | 2022-01-12 | 2022-01-13 | 100% | bar: WEEK 1 (Jan. 9 - 15) S; WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
1.2 | Group meeting | All | 2022-01-15 | 2022-01-15 | Ongoing | bar: WEEK 1 (Jan. 9 - 15) S; WEEK 2 (Jan. 16 - 22) M; WEEK 2 (Jan. 16 - 22) S; WEEK 3 (Jan. 23 - 29) M; WEEK 4 (Jan. 30 - Feb. 5) M; WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S; WEEK 5 (Feb. 6 - 12) M; WEEK 5 (Feb. 6 - 12) S
1.3 | Meeting with project partner | S, M, F, W | 2022-01-20 | 2022-02-20 | Ongoing | bar: WEEK 2 (Jan. 16 - 22) R; WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S; WEEK 6 (Feb. 13 - 19) M
1.4 | Outline tasks and assign roles | S, M, F, W | 2022-01-24 | 2022-01-27 | 100% | bar: WEEK 2 (Jan. 16 - 22) S to WEEK 4 (Jan. 30 - Feb. 5) S
1.5 | Gantt Chart | W, M, F | 2022-01-24 | 2022-01-29 | 100% | bar: WEEK 3 (Jan. 23 - 29) M to WEEK 3 (Jan. 23 - 29) R; WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
1.6 | PPT Presentation | S, M, F, W | 2022-01-29 | 2022-02-10 | 100% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 5 (Feb. 6 - 12) W
1.7 | Project Proposal | All | 2022-01-22 | 2022-02-08 | 95% | bar: WEEK 2 (Jan. 16 - 22) S to WEEK 4 (Jan. 30 - Feb. 5) S
2 | Understanding Data (Progress Report 1)
2.1 | Data Wrangling | Y, S, W, M | 2022-01-08 | 2022-02-12 | 100% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 8 (Feb. 27 - Mar. 5) M
2.2 | Data Cleaning I | Y, S, W, M | 2022-02-08 | 2022-02-15 | 100% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 8 (Feb. 27 - Mar. 5) M
2.3 | Data Analysis |  | 2022-02-08 | 2022-02-17 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
2.4 | Progress Report 1 |  | 2022-02-09 | 2022-03-10 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3 | Project Implementation (Progress Report 2)
3.1 | Data Cleaning II |  | 2022-02-09 | 2022-03-12 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3.2 | Data Prepartion |  | 2022-02-10 | 2022-03-14 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3.3 | Forecasting Model |  | 2022-02-11 | 2022-03-18 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3.4 | Model Evaluation |  | 2022-02-12 | 2022-03-19 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3.5 | User testing and GUI |  | 2022-02-13 | 2022-03-26 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
3.6 | Progress Report 2 |  | 2022-02-14 | 2022-03-31 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
4 | Final Code, Report, and Presentation
4.1 | Modify project based on feedback |  | 2022-02-14 | 2022-04-04 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
4.2 | Report + Presentation |  | 2022-02-15 | 2022-04-11 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S
4.3 | Code + User-guide |  | 2022-02-16 | 2022-04-14 | 0% | bar: WEEK 4 (Jan. 30 - Feb. 5) R to WEEK 4 (Jan. 30 - Feb. 5) S